## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Guest Ordering | 13 |  | 8 | 2 | 2.5 | 1.5 | 2 | 0 | 0 | Done
Create Order and OrderItem database models |  | Brad | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 2
Implement POST /orders to create orders |  | Brad | 3 | 1 | 1.5 | 0.5 | 0 | 0 | 0 | Done | 3
Auto-generate a tracking number |  | Brad | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Done | 1
Support takeout vs delivery |  | Brad | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 1
Basic validation + test request |  | Brad | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 1
Menu Management (CRUD) | 8 |  | 7 | 3.5 | 1.5 | 2 | 0 | 0 | 0 | Done
Create Menu model/schema |  | Brad | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Implement POST /menu |  | Josh | 2 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | Done | 2
Implement GET /menu |  | Josh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Implement DELETE /menu/{id} |  | Josh | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Done | 1
Implement PUT /menu/{id} |  | Josh | 2 | 0 | 0 | 2 | 0 | 0 | 0 | Done | 2
Order Tracking | 8 |  | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Done
Add status field to orders |  | Brad | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Done | 1
Implement GET /orders/tracking/{tracking_number} |  | Kenny | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Done | 2
Set default status (“received”) on order creation |  | Kenny | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Done | 1
View Orders (Staff) | 5 |  | 3 | 0 | 0 | 0 | 3 | 0 | 0 | Done
Implement GET /orders (view all orders) |  | Brad | 2 | 0 | 0 | 0 | 2 | 0 | 0 | Done | 2
Implement GET /orders/{id} (full order details) |  | Brad | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 1
Reviews | 5 |  | 4 | 0 | 0 | 1 | 3 | 0 | 0 | Done
Create Review model/schema |  | Brad | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Done | 0
Implement POST /reviews |  | Maddy | 2 | 0 | 0 | 0 | 2 | 0 | 0 | Done | 0
Implement GET /menu/{id}/reviews |  | Maddy | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 0
TOTAL |  |  | 26 | 7.5 | 5 | 5.5 | 8 | 0 | 0