## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Promo Codes | 5 |  | 6 | 3 | 1 | 1 | 1 | 0 | 0 | Done
Create Promo model |  | Josh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Implement CRUD for /promos |  | Josh | 3 | 1 | 0 | 1 | 1 | 0 | 0 | Done | 3
Add promo code application to order checkout |  | Josh | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 2
Daily Revenue | 3 |  | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done
Implement GET /revenue?date= to sum order totals |  | Robert | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 3
Food Search | 5 |  | 3 | 1 | 2 | 0 | 0 | 0 | 0 | Done
Add category filter to menu GET |  | Maddy | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Implement /menu/search?category= endpoint |  | Maddy | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Done | 2
Ingredient Inventory | 5 |  | 7 | 1 | 1.5 | 2.5 | 1 | 1 | 0 | Done
Create Ingredients table |  | Kenny | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 2
Link menu items → ingredients |  | Kenny | 2 | 0 | 0.5 | 1.5 | 0 | 0 | 0 | Done | 2
On order creation, check ingredient levels |  | Kenny | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | 3
Payment Processing | 8 |  | 6 | 2 | 2 | 1 | 1 | 0 | 0 | Done
Create Payment model |  | Brad | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Implement POST /payments |  | Brad | 3 | 1 | 2 | 0 | 0 | 0 | 0 | Done | 3
Link payments to orders |  | Brad | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 2
Orders by Date Range | 3 |  | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done
Implement GET /orders?start=&end= |  | Robert | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | 3
Documentation | 1 |  | 3 | 1 | 0 | 0 | 0 | 0 | 2 | Done
Complete Presentation |  | Everyone | 2 | 0 | 0 | 0 | 0 | 0 | 2 | Done | 4
Write pytest unit test for POST /menu |  | Josh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 2
TOTAL |  |  | 31 | 9 | 7.5 | 6.5 | 4 | 2 | 2